## 2018 - 2019
Deployment Release Calendar |  |  |  |  | Deployment Release Calendar
| Release 1 (August 16, 2018) |  | Release 2 (August 30, 2018) |  |  | Release 5 (October 11, 2018) |  | Release 6 (October 25, 2018)
| Release Plan¤ | Friday, August 3 | Release Plan¤ | Friday, August 17 |  | Release Plan¤ | Friday, September 28 | Release Plan¤ | Friday, October 12
| Config build complete* | Monday, August 6 | Config build complete* | Monday, 20 |  | Config build complete* | Monday, October 1 | Config build complete* | Monday, October 15
| Development Test Complete* | Wednesday, August 8 | Development Test Complete* | Wednesday, August 22 |  | Development Test Complete* | Wednesday, October 3 | Development Test Complete* | Wednesday, October 17
| Test Migration Complete* | Thursday, August 9 | Test Migration Complete* | Thursday, August 23 |  | Test Migration Complete* | Thursday, October 4 | Test Migration Complete* | Thursday, October 18
| End User Test Complete* | Friday, August 10 | End User Test Complete* | Friday, August 24 |  | End User Test Complete* | Friday, October 5 | End User Test Complete* | Friday, October 19
| Regression Test Complete* | Monday, August 13 | Regression Test Complete* | Monday, August 27 |  | Regression Test Complete* | Monday, October 8 | Regression Test Complete* | Monday, October 22
| Release Approved (CAB) | Tuesday, August 14 | Release Approved (CAB) | Tuesday, August 28 |  | Release Approved (CAB) | Tuesday, October 9 | Release Approved (CAB) | Tuesday, October 23
| PROD Migration Complete (release plan complete) | Wednesday, August 15 | PROD Migration Complete | Wednesday, August 29 |  | PROD Migration Complete | Wednesday, October 10 | PROD Migration Complete | Wednesday, October 24
| Production Implementation | Thursday, Aug 16 - Sunday, Aug 19 | Production Implementation | Thursday, Aug 30 - Sunday, Sep 2 |  | Production Implementation | Thursday, Oct 11 - Sunday, Oct 14 | Production Implementation | Thursday, Oct 25 - Sunday, Oct 28
| Release 3 (September 13, 2018) |  | Release 4 (September 27, 2018) |  |  | Release 7 (November 8, 2018) |  | Release 8 (November 22, 2018)
| Release Plan¤ | Friday, August 31 | Release Plan¤ | Friday, September 14 |  | Release Plan¤ | Friday, October 26 | Release Plan¤ | Friday, November 9
| Config build complete* | Monday, September 3 | Config build complete* | Monday, September 17 |  | Config build complete* | Monday, October 29 | Config build complete* | Monday, November 12
| Development Test Complete* | Wednesday, September 5 | Development Test Complete* | Wednesday, September 19 |  | Development Test Complete* | Wednesday, October 31 | Development Test Complete* | Wednesday, November 14
| Test Migration Complete* | Thursday, September 6 | Test Migration Complete* | Thursday, September 20 |  | Test Migration Complete* | Thursday, November 1 | Test Migration Complete* | Thursday, November 15
| End User Test Complete* | Friday, September 7 | End User Test Complete* | Friday, September 21 |  | End User Test Complete* | Friday, November 2 | End User Test Complete* | Friday, November 16
| Regression Test Complete* | Monday, September 10 | Regression Test Complete* | Monday, September 24 |  | Regression Test Complete* | Monday, November 5 | Regression Test Complete* | Monday, November 19
| Release Approved (CAB) | Tuesday, September 11 | Release Approved (CAB) | Tuesday, September 25 |  | Release Approved (CAB) | Tuesday, November 6 | Release Approved (CAB) | Tuesday, November 20
| PROD Migration Complete | Wednesday, September 12 | PROD Migration Complete | Wednesday, September 26 |  | PROD Migration Complete | Wednesday, November 7 | PROD Migration Complete | Wednesday, November 21
| Production Implementation | Thursday, Sep 13 - Sunday, Sep 16 | Production Implementation | Thursday, Sep 27 - Sunday, Sep 30 |  | Production Implementation | Thursday, Nov 8 - Sunday, Nov 11 | Production Implementation | Thursday, Nov 22 - Sunday, Nov 25
| ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility |  |  |  |  | ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility
Deployment Release Calendar |  |  |  |  | Deployment Release Calendar
| Release 9 (December 6, 2018) |  | Release 10 (December 20, 2018) |  |  | Release 13 (February 7, 2019) |  | Release 14 (February 21, 20189)
| Release Plan¤ | Monday, November 26 | Release Plan¤ | Friday, December 7 |  | Release Plan¤ | Friday, January 25 | Release Plan¤ | Friday, February 8
| Config build complete* | Tuesday, November 27 | Config build complete* | Monday, December 10 |  | Config build complete* | Monday, January 28 | Config build complete* | Monday, February 11
| Development Test Complete* | Wednesday, November 28 | Development Test Complete* | Wednesday, December 12 |  | Development Test Complete* | Wednesday, January 30 | Development Test Complete* | Wednesday, December 12
| Test Migration Complete* | Thursday, November 29 | Test Migration Complete* | Thursday, December 13 |  | Test Migration Complete* | Thursday, January 31 | Test Migration Complete* | Thursday, February 13
| End User Test Complete* | Friday, November 30 | End User Test Complete* | Friday, December 14 |  | End User Test Complete* | Friday, February 1 | End User Test Complete* | Friday, February 15
| Regression Test Complete* | Monday, December 3 | Regression Test Complete* | Monday, December 17 |  | Regression Test Complete* | Monday, February 4 | Regression Test Complete* | Monday, February 18
| Release Approved (CAB) | Tuesday, December 4 | Release Approved (CAB) | Tuesday, December 18 |  | Release Approved (CAB) | Tuesday, February 5 | Release Approved (CAB) | Tuesday, February 19
| PROD Migration Complete | Wednesday, December 5 | PROD Migration Complete | Wednesday, December 19 |  | PROD Migration Complete | Wednesday, February 6 | PROD Migration Complete | Wednesday February 20
| Production Implementation | Thursday, Dec 6 - Sunday, Dec 9 | Production Implementation | Thursday, Dec 20 - Sunday, Dec 23 |  | Production Implementation | Thursday, Feb 7 - Sunday, Feb 10 | Production Implementation | Thursday, Feb 21 - Sunday, Feb 24
| Release 11 (January 10, 2019) |  | Release 12 (January 24, 2019) |  |  | Release 15 (March 7, 2019) |  | Release 16 (March 21, 2019)
| Release Plan¤ | Friday, December 21 | Release Plan¤ | Friday, January 11 |  | Release Plan¤ | Friday, February 22 | Release Plan¤ | Friday, March 8
| Config build complete* | Wednesday, January 2 | Config build complete* | Monday, January 14 |  | Config build complete* | Monday, February 25 | Config build complete* | Monday, March 11
| Development Test Complete* | Wednesday, January 2 | Development Test Complete* | Wednesday, January 16 |  | Development Test Complete* | Wednesday, February 27 | Development Test Complete* | Wednesday, March 13
| Test Migration Complete* | Thursday, January 3 | Test Migration Complete* | Thursday, January 17 |  | Test Migration Complete* | Thursday, February 28 | Test Migration Complete* | Thursday, March 14
| End User Test Complete* | Friday, January 4 | End User Test Complete* | Friday, January 18 |  | End User Test Complete* | Friday, March 1 | End User Test Complete* | Friday, March 15
| Regression Test Complete* | Monday, January 7 | Regression Test Complete* | Friday, January 18 |  | Regression Test Complete* | Monday, March 4 | Regression Test Complete* | Monday, March 18
| Release Approved (CAB) | Tuesday, January 8 | Release Approved (CAB) | Tuesday, January 22 |  | Release Approved (CAB) | Monday, March 4 | Release Approved (CAB) | Tuesday, March 19
| PROD Migration Complete | Wednesday, January 9 | PROD Migration Complete | Wednesday, January 23 |  | PROD Migration Complete | Wednesday, March 6 | PROD Migration Complete | Wednesday, March 20
| Production Implementation | Thursday, Jan 10 - Sunday, Jan 13 | Production Implementation | Thursday, Jan 24 - Sunday, Jan 27 |  | Production Implementation | Thursday, Mar 7 - Sunday, Mar 10 | Production Implementation | Thursday, Mar 21 - Sunday, Mar 24
| ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility |  |  |  |  | ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility
Deployment Release Calendar |  |  |  |  | Deployment Release Calendar
| Release 17 (April 4, 2019) |  | Release 18 (April 18, 2019) |  |  | Release 21 (May 30, 2019) |  | Release 22 (June 13, 2019)
| Release Plan¤ | Friday, March 22 | Release Plan¤ | Friday, April 5 |  | Release Plan¤ | Friday, May 17 | Release Plan¤ | Friday, May 31
| Config build complete* | Monday, March 25 | Config build complete* | Monday, April 8 |  | Config build complete* | Monday, May 20 | Config build complete* | Monday, June 3
| Development Test Complete* | Wednesday, March 27 | Development Test Complete* | Wednesday, April 10 |  | Development Test Complete* | Wednesday, May 22 | Development Test Complete* | Wednesday, June 5
| Test Migration Complete* | Thursday, March 28 | Test Migration Complete* | Thursday, April 11 |  | Test Migration Complete* | Thursday, May 23 | Test Migration Complete* | Thursday, June 6
| End User Test Complete* | Friday, March 29 | End User Test Complete* | Friday, April 12 |  | End User Test Complete* | Friday, May 24 | End User Test Complete* | Friday, June 7
| Regression Test Complete* | Monday, April 1 | Regression Test Complete* | Monday, April 15 |  | Regression Test Complete* | Monday, May 27 | Regression Test Complete* | Monday, June 10
| Release Approved (CAB) | Tuesday, April 2 | Release Approved (CAB) | Tuesday, April 16 |  | Release Approved (CAB) | Tuesday, May 28 | Release Approved (CAB) | Tuesday, June 11
| PROD Migration Complete | Wednesday, April 3 | PROD Migration Complete | Wednesday, April 17 |  | PROD Migration Complete | Wednesday, May 29 | PROD Migration Complete | Wednesday, June 12
| Production Implementation | Thursday, Apr 4 - Sunday, Apr 7 | Production Implementation | Thursday, Apr 18 - Sunday, Apr 21 |  | Production Implementation | Thursday, May 30 - Sunday, Jun 2 | Production Implementation | Thursday, Jun 13 - Sunday, Jun 16
| Release 19 (May 2, 2019) |  | Release 20 (May 16, 2019) |  |  | Release 23 (June 27, 2019)
| Release Plan¤ | Friday, April 19 | Release Plan¤ | Friday, May 3 |  | Release Plan¤ | Friday, June 14
| Config build complete* | Monday, April 22 | Config build complete* | Monday, May 6 |  | Config build complete* | Monday, June 17
| Development Test Complete* | Wednesday, April 24 | Development Test Complete* | Wednesday, May 8 |  | Development Test Complete* | Wednesday, June 19
| Test Migration Complete* | Thursday, April 25 | Test Migration Complete* | Thursday, May 9 |  | Test Migration Complete* | Thursday, June 20
| End User Test Complete* | Friday, April 26 | End User Test Complete* | Friday, May 10 |  | End User Test Complete* | Friday, June 21
| Regression Test Complete* | Monday, April 29 | Regression Test Complete* | Monday, May 13 |  | Regression Test Complete* | Monday, June 24
| Release Approved (CAB) | Tuesday, April 30 | Release Approved (CAB) | Tuesday, May 14 |  | Release Approved (CAB) | Tuesday, June 25
| PROD Migration Complete | Wednesday, May 1 | PROD Migration Complete | Wednesday, May 15 |  | PROD Migration Complete | Wednesday, June 26
| Production Implementation | Thursday, May 2 - Sunday, May 5 | Production Implementation | Thursday, May 16 - Sunday, May 19 |  | Production Implementation | Thursday, Jun 27 - Sunday, Jun 30
| ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility |  |  |  |  | ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility

## 2019-2020
Deployment Release Calendar |  |  |  |  | Deployment Release Calendar
| Release 1 (July 11, 2019) |  | Release 2 (July 25, 2019) |  |  | Release 5 (September 5, 2019) |  | Release 6 (September 19, 2019)
| Release Plan¤ | Friday, June 28 | Release Plan¤ | Friday, July 12 |  | Release Plan¤ | Friday, August 23 | Release Plan¤ | Friday, September 6
| Config build complete* | Monday, July 1 | Config build complete* | Monday, 15 |  | Config build complete* | Monday, August 26 | Config build complete* | Monday, September 9
| Development Test Complete* | Wednesday, July 3 | Development Test Complete* | Wednesday, July 17 |  | Development Test Complete* | Wednesday, August 28 | Development Test Complete* | Wednesday, September 11
| Test Migration Complete* | Wednesday, July 3 | Test Migration Complete* | Thursday, July 18 |  | Test Migration Complete* | Thursday, August 29 | Test Migration Complete* | Thursday, September 12
| End User Test Complete* | Friday, July 5 | End User Test Complete* | Friday, July 19 |  | End User Test Complete* | Friday, August 30 | End User Test Complete* | Friday, September 13
| Regression Test Complete* | Monday, July 8 | Regression Test Complete* | Monday, July 22 |  | Regression Test Complete* | Tuesday, September 3 | Regression Test Complete* | Monday, September 16
| Release Approved (CAB) | Tuesday, July 9 | Release Approved (CAB) | Tuesday, July 23 |  | Release Approved (CAB) | Tuesday, September 3 | Release Approved (CAB) | Tuesday, September 17
| PROD Migration Complete (release plan complete) | Wednesday, July 10 | PROD Migration Complete | Wednesday, July 24 |  | PROD Migration Complete | Wednesday, September 4 | PROD Migration Complete | Wednesday, September 18
| Production Implementation | Thursday, July 11 - Sunday, July 14 | Production Implementation | Thursday, July 25 - Sunday, July 28 |  | Production Implementation | Thursday, Sept 5 - Sunday, Sept 8 | Production Implementation | Thursday, Sept 19 - Sunday, Sept 22
| Release 3 (August 8, 2019) |  | Release 4 (August 22, 2019) |  |  | Release 7 (October 3, 2019) |  | Release 8 (October 17, 2019)
| Release Plan¤ | Friday, July 26 | Release Plan¤ | Friday, August 9 |  | Release Plan¤ | Friday, September 20 | Release Plan¤ | Friday, October 4
| Config build complete* | Monday, July 29 | Config build complete* | Monday, August 12 |  | Config build complete* | Monday, September 23 | Config build complete* | Monday, October 7
| Development Test Complete* | Wednesday, July 31 | Development Test Complete* | Wednesday, August 14 |  | Development Test Complete* | Wednesday, September 25 | Development Test Complete* | Wednesday, October 9
| Test Migration Complete* | Thursday, August 1 | Test Migration Complete* | Thursday, August 15 |  | Test Migration Complete* | Thursday, September 26 | Test Migration Complete* | Thursday, October 10
| End User Test Complete* | Friday, August 2 | End User Test Complete* | Friday, August 16 |  | End User Test Complete* | Friday, September 27 | End User Test Complete* | Friday, October 11
| Regression Test Complete* | Monday, August 5 | Regression Test Complete* | Monday, August 19 |  | Regression Test Complete* | Monday, September 30 | Regression Test Complete* | Monday, October 14
| Release Approved (CAB) | Tuesday, August 6 | Release Approved (CAB) | Tuesday, August 20 |  | Release Approved (CAB) | Tuesday, October 2 | Release Approved (CAB) | Tuesday, October 15
| PROD Migration Complete | Wednesday, August 7 | PROD Migration Complete | Wednesday, August 21 |  | PROD Migration Complete | Wednesday, November 6 | PROD Migration Complete | Wednesday, October 16
| Production Implementation | Thursday, Aug 8 - Sunday, Aug 11 | Production Implementation | Thursday, Aug 22 - Sunday, Aug 25 |  | Production Implementation | Thursday, Oct 3 - Sunday, Oct 6 | Production Implementation | Thursday, Oct 17 - Sunday, Oct 20
| ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility |  |  |  |  | ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility
Deployment Release Calendar |  |  |  |  | Deployment Release Calendar
| Release 9 (October 31, 2019) |  | Release 10 (November 14, 2019) |  |  | Release 13 (January 9, 2020) |  | Release 14 (January 23, 2020)
| Release Plan¤ | Friday, October 18 | Release Plan¤ | Friday, November 1 |  | Release Plan¤ | Thursday, December 19 | Release Plan¤ | Friday, January 10
| Config build complete* | Monday, October 21 | Config build complete* | Monday, November 4 |  | Config build complete* | Friday, December 20 | Config build complete* | Monday, January 13
| Development Test Complete* | Wednesday, October 23 | Development Test Complete* | Wednesday, November 6 |  | Development Test Complete* | Monday, December 23 | Development Test Complete* | Wednesday, January 15
| Test Migration Complete* | Thursday, October 24 | Test Migration Complete* | Thursday, November 7 |  | Test Migration Complete* | Thursday, January 2 | Test Migration Complete* | Thursday, January 16
| End User Test Complete* | Friday, October 25 | End User Test Complete* | Friday, November 8 |  | End User Test Complete* | Friday, January 3 | End User Test Complete* | Friday, January 17
| Regression Test Complete* | Monday, October 28 | Regression Test Complete* | Monday, November 11 |  | Regression Test Complete* | Monday, January 6 | Regression Test Complete* | Tuesday, January 21
| Release Approved (CAB) | Tuesday, October 29 | Release Approved (CAB) | Tuesday, November 12 |  | Release Approved (CAB) | Tuesday, January 7 | Release Approved (CAB) | Tuesday, January 21
| PROD Migration Complete | Wednesday, October 30 | PROD Migration Complete | Wednesday, November 13 |  | PROD Migration Complete | Wednesday, January 8 | PROD Migration Complete | Wednesday January 22
| Production Implementation | Thursday, Oct 31 - Sunday, Nov 3 | Production Implementation | Thursday, Nov 14 - Sunday, Nov 17 |  | Production Implementation | Thursday, Jan 9 - Sunday, Jan 12 | Production Implementation | Thursday, Jan 23 - Sunday, Jan 26
| Release 11 (December 5, 2019) |  | Release 12 (December 19, 2019) |  |  | Release 15 (February 6, 2020) |  | Release 16 (February 20, 2020)
| Release Plan¤ | Friday, November 15 | Release Plan¤ | Friday, December 6 |  | Release Plan¤ | Friday, January 24 | Release Plan¤ | Friday, February 7
| Config build complete* | Monday, November 18 | Config build complete* | Monday, December 9 |  | Config build complete* | Monday, January 27 | Config build complete* | Monday, February 10
| Development Test Complete* | Wednesday, November 20 | Development Test Complete* | Wednesday, December 11 |  | Development Test Complete* | Wednesday, January 29 | Development Test Complete* | Wednesday, February 12
| Test Migration Complete* | Thursday, November 21 | Test Migration Complete* | Thursday, December 12 |  | Test Migration Complete* | Thursday, January 30 | Test Migration Complete* | Thursday, February 13
| End User Test Complete* | Friday, Novemebr 22 | End User Test Complete* | Friday, December 13 |  | End User Test Complete* | Friday, January 31 | End User Test Complete* | Friday, February 14
| Regression Test Complete* | Monday, November 25 | Regression Test Complete* | Monday December 16 |  | Regression Test Complete* | Monday, February 3 | Regression Test Complete* | Monday, February 17
| Release Approved (CAB) | Tuesday, November 26 | Release Approved (CAB) | Tuesday, December 17 |  | Release Approved (CAB) | Tuesday, February 4 | Release Approved (CAB) | Tuesday, February 18
| PROD Migration Complete | Wednesday, December 4 | PROD Migration Complete | Wednesday, December 18 |  | PROD Migration Complete | Wednesday, February 5 | PROD Migration Complete | Wednesday, February 19
| Production Implementation | Thursday, Dec 5 - Sunday, Dec 8 | Production Implementation | Thursday, Dec 19 - Dec 22 |  | Production Implementation | Thursday, Feb 6 - Sunday, Feb 9 | Production Implementation | Thursday, Feb 20 - Sunday, Feb 24
| ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility |  |  |  |  | ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility
Deployment Release Calendar |  |  |  |  | Deployment Release Calendar
| Release 17 (March 5, 2020) |  | Release 18 (March 19, 2020) |  |  | Release 21 (April 30, 2020) |  | Release 22 (May 14, 2020)
| Release Plan¤ | Friday, February 21 | Release Plan¤ | Friday, March 6 |  | Release Plan¤ | Friday, April 17 | Release Plan¤ | Friday, May 1
| Config build complete* | Monday, February 24 | Config build complete* | Monday, March 9 |  | Config build complete* | Monday, April 20 | Config build complete* | Monday, May 4
| Development Test Complete* | Wednesday, February 26 | Development Test Complete* | Wednesday, March 11 |  | Development Test Complete* | Wednesday, April 22 | Development Test Complete* | Wednesday, May 6
| Test Migration Complete* | Thursday, February 27 | Test Migration Complete* | Thursday, March 12 |  | Test Migration Complete* | Thursday, April 23 | Test Migration Complete* | Thursday, May 7
| End User Test Complete* | Friday, February 28 | End User Test Complete* | Friday, March 13 |  | End User Test Complete* | Friday, April 24 | End User Test Complete* | Friday, May 8
| Regression Test Complete* | Monday, March 2 | Regression Test Complete* | Monday, March 16 |  | Regression Test Complete* | Monday, April 27 | Regression Test Complete* | Monday, May 11
| Release Approved (CAB) | Tuesday, March 3 | Release Approved (CAB) | Tuesday, March 17 |  | Release Approved (CAB) | Tuesday, April 28 | Release Approved (CAB) | Tuesday, May 12
| PROD Migration Complete | Wednesday, March 4 | PROD Migration Complete | Wednesday, March 18 |  | PROD Migration Complete | Wednesday, April 29 | PROD Migration Complete | Wednesday, May 13
| Production Implementation | Thursday, Mar 5 - Sunday, Mar 8 | Production Implementation | Thursday, Mar 19 - Sunday, Mar 22 |  | Production Implementation | Thursday, April 30 - Sunday, May 3 | Production Implementation | Thursday, May 14 - Sunday, May 17
| Release 19 (April 2, 2020) |  | Release 20 (April 16, 2020) |  |  | Release 23 (May 28, 2020) |  | Release 24 (June 11, 2020)
| Release Plan¤ | Friday, March 20 | Release Plan¤ | Friday, April 3 |  | Release Plan¤ | Friday, May 15 | Release Plan¤ | Friday, May 29
| Config build complete* | Monday, March 23 | Config build complete* | Monday, April 6 |  | Config build complete* | Monday, May 18 | Config build complete* | Monday, June 1
| Development Test Complete* | Wednesday, March 25 | Development Test Complete* | Wednesday, April 8 |  | Development Test Complete* | Wednesday, May 20 | Development Test Complete* | Wednesday, June 3
| Test Migration Complete* | Thursday, March 26 | Test Migration Complete* | Thursday, April 9 |  | Test Migration Complete* | Thursday, May 21 | Test Migration Complete* | Thursday, June 4
| End User Test Complete* | Friday, March 27 | End User Test Complete* | Thursday, April 9 |  | End User Test Complete* | Friday, May 22 | End User Test Complete* | Friday, June 5
| Regression Test Complete* | Monday, March 30 | Regression Test Complete* | Monday, April 13 |  | Regression Test Complete* | Monday, May 25 | Regression Test Complete* | Monday, June 8
| Release Approved (CAB) | Tuesday, March 31 | Release Approved (CAB) | Tuesday, April 14 |  | Release Approved (CAB) | Tuesday, May 26 | Release Approved (CAB) | Tuesday, June 9
| PROD Migration Complete | Wednesday, April 1 | PROD Migration Complete | Wednesday, April 15 |  | PROD Migration Complete | Wednesday, May 27 | PROD Migration Complete | Wednesday, June 10
| Production Implementation | Thursday, Apr 2 - Sunday, Apr 5 | Production Implementation | Thursday, Apr 16 - Sunday, Apr 19 |  | Production Implementation | Thursday, May 28 - Sunday, May 31 | Production Implementation | Thursday, Jun 11 - Sunday, Jun 14
| ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility |  |  |  |  | ¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility
Deployment Release Calendar
Release 25 (June 25, 2020)
| Release Plan¤ | Friday, June 12
| Config build complete* | Monday, June 15
| Development Test Complete* | Wednesday, June 17
| Test Migration Complete* | Thursday, June 18
| End User Test Complete* | Friday, June 19
| Regression Test Complete* | Monday, June 22
| Release Approved (CAB) | Tuesday, June 23
| PROD Migration Complete | Wednesday, June 24
| Production Implementation | Thursday, Jun 25 - Sunday, Jun 28
¤ Release Plan – Items in scope of the release (final CAB authorization must be completed by this date) • If Regression Testing is not complete on the assigned date and ready for PROD, the change will have to move to another Release * If applicable, implementation area's responsibility